## Sheet1
Overview Budget
Category | Product Cost
Personnel Costs | 72000
Fixed Costs | 15500
Contigency Costs | 8750
Overall Project Budget | 96250
Personnel Costs (because team work has 4 sprints with 2 weeks lasting and 40 hr working hours)
Role | Hourly Rate | Hours per Sprint | Sprints | Total Cost
Product Owner | 60 | 80 | 4 | 19200
Scrum Master | 50 | 80 | 4 | 16000
Developer | 45 | 160 | 4 | 28800
UI/UX Designer | 40 | 80 | 4 | 12800
QA Specialist | 40 | 80 | 4 | 12800
Total Personnel Cost |  |  |  | 72000
Fixed Costs
Description | Cost | Frequency | Total Cost
Project Management Tools (e.g., Jira) | 300 | Per Sprint | 1200
Cloud Hosting (e.g., AWS) | 1500 | Per Month | 6000
Backend API Service | 1000 | Per Month | 4000
Database Licensing (e.g., Firebase) | 250 | Per Sprint | 1000
Equipment (Developer laptops) | 3300 | One-time | 3300
Total Fixed Cost |  |  | 15500
Contingency Costs
Category | Percentage of Budget | Contingency Amount
Personnel | 5% | 3600
Fixed Costs | 5% | 750
Total Contingency |  | 8750